Changing this number will scroll the Gantt Chart view.
## ProjectSchedule
Create a Project Schedule in this worksheet. / Enter title of this project in cell B1. / Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. / Continue navigating down column A to hear further instructions.	EZSHOP
Enter Company Name in cell B2.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3.		Project Start:	sex, 3/5/2021
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. / The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. / You should not modify these cells. / Display Week: label is in cell C4.		Display Week:	13				mai 24, 2021					mai 31, 2021					jun 7, 2021					jun 14, 2021					jun 21, 2021					jun 28, 2021					jul 5, 2021					jul 12, 2021
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. / You should not modify these cells. / Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule.						24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18
This row contains headers for the project schedule that follows below them. / Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. / All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. / Do not modify content in cells within columns after column I starting with cell I7.	TASK	ASSIGNED / TO	START	END		DAYS	s	t	q	q	s	s	d	s	t	q	q	s	s	d	s	t	q	q	s	s	d	s	t	q	q	s	s	d	s	t	q	q	s	s	d	s	t	q	q	s	s	d	s	t	q	q	s	s	d	s	t	q	q	s	s	d
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
	Sprint 4
	Login e registo	Ambos	6/8/21	6/12/21
	Criar e remover listas de compras	Ambos	6/13/21	6/14/21
	Obter Listas de utilizador ao fazer login	Ambos	6/15/21	6/17/21
	Marcar um item como comprado	Ambos	6/18/21	6/19/21
	Adcionar produto de uma lista - Interface	Ambos	6/20/21	6/23/21
	Adicionar e remover produto de uma lista	Ambos	6/24/21	6/26/21
	Adicionar à lista a partir do reconhecimento	Ambos	6/27/21	7/1/21
	Adicionar e remover produto de uma lista	Ambos	7/2/21	7/5/21
	Documentar REST API	Francisco	7/6/21	7/14/21
	Ver e alterar detalhes de um Produto	Ambos	7/6/21	7/9/21
	Partilha de uma lista com outros utilizadores	Ambos	7/10/21	7/15/21
	Melhorar e implementar verificações na aplicação	Luís	7/10/21	7/10/21
	Fazer o Icone da aplicação	Ambos	7/11/21	7/13/21
	Fazer manual de utilizador	Francisco	7/10/21	7/10/21
	Fase de testes	Ambos	7/11/21	7/13/21
	Utilizador enviar multiplas imagens de um produto.	Luís	7/11/21	7/13/21
	Fazer documentação e rever projeto	Ambos	7/13/21	7/16/21
	Manual de Identidade Visual	Luís	7/16/21	7/16/21
	Sprint 3
	Projeção da base de dados	Ambos	5/11/21	5/12/21
	Pré-processamento dados a utilizar no modelo	Ambos	5/13/21	5/16/21
	Trabalhar o modelo para ser implementado	Ambos	5/17/21	5/20/21
	Interface reconhecer produto e explorar câmara	Luís	5/20/21	5/25/21
	Desenvolvimento do backend	Francisco	5/23/21	6/5/21
	Implementar reconhecimento de produtos	Luís	5/26/21	5/31/21
	Juntar imagens para treinar e testar o modelo	Ambos	6/1/21	6/1/21
	Interfaces de login e registo	Francisco	6/2/21	6/5/21
	Interface e lógica da pesquisa de produtos	Luís	6/2/21	6/5/21
	Documentação	Ambos	6/4/21	6/6/21
	Sprint 2:
	Análise de requisitos a partir do estado da arte	Ambos	4/14/21	4/17/21
	Criar lista de requisitos	Francisco	4/18/21	4/25/21
	Prototipagem da aplicação	Ambos	4/22/21	5/1/21
	Início do desenvolvimento das interfaces	Luís	4/28/21	5/6/21
	Fazer documentação	Ambos	5/7/21	5/9/21
	Sprint 1:
	Definir ideia do projeto	Ambos	3/5/21	3/10/21
	Atribuir nome ao Projeto	Ambos	3/10/21	3/11/21
	Estado da arte (aplicações)	Francisco	3/10/21	3/20/21
	Estado da arte (Reconhecimento de imagens)	Luís	3/10/21	3/20/21
	Testes na geração de modelos no tensorflow	Ambos	3/15/21	3/30/21
	API para recolha de imagens	Luís	3/23/21	3/23/21
	Fazer documentação	Ambos	3/30/21	4/12/21

This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. / Insert new rows ABOVE this one to continue building out your Project Schedule.	Insert new rows ABOVE this one

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. / TimeSheet / About / The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. / This hidden text will not print. / To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.